## Schedule
Phase | Activity | Start Day | End Day | Duration | Depends On | Deliverable | Owner
Planning | Define objectives & scope | 1 | 2 | 2 | — | Scope statement | PM
Design | Develop system architecture | 3 | 5 | 3 | Planning | Architecture document | Architecture Lead
Analysis | Perform risk assessment | 6 | 7 | 2 | Design | Risk register | Risk Manager
Project planning | Develop schedule and plans | 8 | 9 | 2 | Analysis | PM plan | PM
Integration | Compile and unify document | 10 | 11 | 2 | All phases | Integrated PDF | Implementation Lead
Delivery | Final review and submission | 12 | 12 | 1 | Integration | Final submission | PM
Total |  |  |  | 12

## Gantt Chart
Phase / Activity | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12
Milestones | D1: M1; D5: M2; D7: M3; D11: M4; D12: M5
Planning: Define objectives & scope | bar: D1 to D2
Design: Develop system architecture | bar: D3 to D5
Analysis: Perform risk assessment | bar: D6 to D7
Project planning: Develop schedule and plans | bar: D8 to D9
Integration: Compile and unify document | bar: D10 to D11
Delivery: Final review and submission | bar: D12
Legend
Phase bar | bar: D1
Milestone | bar: D1

## Milestones
ID | Day | Name | Description
M1 | 1 | Project Start | Kick-off — team aligned, scope and roles confirmed
M2 | 5 | Architecture Completed | Architecture and quality framework signed off
M3 | 7 | Risk Analysis Completed | Risk register reviewed and accepted
M4 | 11 | Document Integration Completed | All sections compiled into a single PDF
M5 | 12 | Final Submission | Submission to course platform and final commit to GitHub

## Critical Path
Critical Path
Planning → Design → Analysis → Project Planning → Integration → Delivery
Any slippage on the activities above directly displaces the submission date because each phase consumes outputs of the previous one — there is no parallel float available.