## Risk Register
ID | Risk | Category | Probability | Impact | Level | Mitigation | Contingency | Monitoring | Quality Attribute
R1 | System overload | Technical | High | High | Critical | Kubernetes auto-scaling; priority queues | Scale services manually; shed non-critical traffic | Prometheus + Grafana alerts on request latency | Scalability
R2 | Notification failure | Technical | Medium | High | High | SMS + Push redundancy; DLQ retry strategy | Switch to surviving channel; replay from DLQ | Provider health checks every 30 s | Reliability
R3 | False reports | Security | High | Medium | High | Heuristic verification; user reputation scoring | Hold suspicious alerts for human review | False-positive rate dashboard | Integrity
R4 | Data breach | Security | Low | Critical | High | TLS 1.3, AES-256 at rest, RBAC, audit logging | Rotate credentials; isolate service; legal notification within 72h | SIEM with anomaly detection | Security
R5 | Low adoption | Operational | Medium | High | High | Usability improvements; onboarding campaigns | Targeted communications; ambassadors program | Monthly active users dashboard | Usability
R6 | Connectivity issues | Operational | High | Medium | High | SMS / USSD fallback channel | Route all alerts through SMS provider | Coverage map and dropped-message metrics | Availability
R7 | Integration failure (3rd-party) | Technical | Medium | High | High | API redundancy; circuit breakers | Failover to secondary provider | Provider status APIs and synthetic checks | Reliability
R8 | Slow authority response | Operational | Medium | High | High | Escalation protocols; SLA agreements | Auto-escalate to next responder tier | Authority response time tracking | Performance
R9 | Poor UX | Project | Medium | Medium | Medium | UX testing; iterative design reviews | Hot-fix releases; usability sprints | User satisfaction surveys; funnel analytics | Usability
R10 | Database failure | Technical | Low | Critical | High | Primary--standby replication; daily backups | Promote standby; restore from backup | Replication lag and backup-success alerts | Reliability

## Heat Map
Probability \ Impact | Low | Medium | High
Low | Low | Low | R4, R10
Medium | Low | R9 | R2, R5, R7, R8
High | Medium | R3, R6 | R1

## Legend
CSAS — Workshop No. 3 Risk Register
Document | Workshop 3 — Robust System Design and Project Management
Project | Community Security Alert System (CSAS)
Course | Systems Analysis & Design — Semester 2026-I
Institution | Universidad Distrital Francisco José de Caldas
Frameworks | ISO 31000:2018, PMBOK 7th ed., ISO/IEC 25010
Severity Levels
Critical | Probability=High AND Impact=High
High | (Prob+Impact) reaches a high score
Medium | Mid-range probability and impact
Low | Low probability and impact